## LESSONS LEARNED
LESSONS LEARNED
PROJECT NAME | Event Recommender System Project for Employees
PROJECT ID
PROJECT MANAGER | Jayanth G S
PROJECT SPONSOR | None
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2020-07-15 | Problem statement not undertood properly at first which lead to confusion for solution | Learned | None | Understanding problem statement | understood the problem statement what is expected | Hritik Sharma | Closed | None
2 | 2020-07-20 | Deciding which algorithm should be used and what approach should be used which was quite hard | Scope | Yes | Studying whole data available | .Deside to use NLP | Hritik Sharma | Closed | None
3 | 2020-07-22 | Checking project is feasible or not it may harm planning if feasibility study goes wrong | Feasibility | None | Keep on checking are we going right or not that will help to know is this approach is feasible or not or is this project itself feasible or not | Checked feasibility and changed approach for multiple times | Hritik Sharma | Closed | None
4 | 2020-07-25 | System and hardware | Resource | Yes | Sometimes hardware or software we are using is not compatible for work expected from them so check compatibility before starting work. | No action required | Hritik Sharma | Closed | None