## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Event Recommender System Project by Employees
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 15/06/2020
EXPECTED COMPLETION DATE | 31/07/2020
ESTIMATED COST | 0
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | The aim is to create a Recommender System that recommends only relevant event to each employee and intern based on their preferences whenever the company receives an invite for a particular event , the system should read new event and autonomouly classify them into specific domain.
BUSINESS CASE | Many employees delivers many projects for its clients and internally as well. To bring about consistency in the way we deliver our projects, which helps our client and our team understand the approach that needs to be taken to deliver these projects.
GOALS/METRICS | Creating a recommendation system that recommends the relevent event to employees
EXPECTED DELIVERABLES | It will be benificial for interns and employees
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | To suggest a particular event to the interns and employees
OUTSIDE OF SCOPE | Recommending event to the employees and interns that is not in the recommendation list
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Alone
SUPPORT RESOURCES | Youtube
SPECIAL NEEDS | Python 3.6
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Hritik Sharma
KEY STAKEHOLDERS | Jayanth GS , Nirbhey Singh Pahwa , Aarya Bodhankar
END CUSTOMER | XYZ Companies
EXPECTED BENEFIT | To develop a recommender system that recommends Events to Employees on there preferences
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS
ASSUMPTIONS | User will always enter domain name as specified in the Employee CSV File
CONSTRAINTS