## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Event Recommender System project for employees
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE:
PROJECT DELIVERABLE | for company employees |  | EXECUTION PHASE END DATE:
PROJECT SCOPE | Python3.7
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | 100%
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
Research on Problem Statement | Findings of libraries, Dataset, etc | 5 | 2020-06-17 | 2020-06-20 | 3 | COMPLETED
Development | Importing Libraires and Dataset | 3 | 2020-06-22 | 2020-06-26 | 4 | COMPLETED
Completion of Code | Used the libraries with their features | 18 | 2020-06-29 | 2020-07-06 | 8 | COMPLETED
Debugging | Debuged the code | 8 | 2020-07-10 | 2020-07-15 | 6 | COMPLETED